PROJECT BRIEF

Project Title			: 	Integrated Management of Acute Malnutrition

Location			:	Province-wide

Implementing Agency		:	Provincial Health Office

Start Date and Duration	: 	Jan 2020 to December 2022

Project Cost			:	P

I.	Rationale

The 2015 National Nutrition Survey (NNS) estimates acute malnutrition/wasting among under-five years old Filipino children at 7.1%.  This is equivalent to about 1 million children and is considered a public health significance. Regional wasting prevalence is also 7.1%.

Severe and moderate acute malnutrition or wasting is associated with increased risk of health and nutrition deterioration and even death for infants and young children, in addition to growth retardation and impaired psychosocial and cognitive development. In the long run, it results to overall poor individual productivity and economic gains.

Based on same 2015 NNS, the prevalence of wasting of children under-five years old in the province is 7.3% - higher than the national prevalence, and affecting an estimated 9,967 children. This lists Zamboanga del Norte as the province with the highest prevalence of wasting in the Zamboanga Peninsula region.

Yet, acute malnutrition is preventable and treatable but only when sufficient support is accessible and given at the right time during calamities and even in normal situations. Services for the treatment and management of severe acute malnutrition (SAM) and moderate acute malnutrition (MAM) are delivered through in-patient treatment centers, out-patient treatment centers and target supplementary feeding program sites.

Given this alarming situation and in support to the PPAN program Philippine Integrated Management of Acute Malnutrition or PIMAM, there is a need for the province to establish and/or strengthen the integrated management of acute malnutrition (IMAM)) within the health system to achieve set service targets and deliver outcomes.

The IMAM project will entail three major complementary activities: 1) establishment of inpatient therapeutic care (ITC) for SAM and outpatient therapeutic care (OTC) for SAM and MAM as well as support the establishment of the same in the priority constituent LGUs; 2) training of health and nutrition human resource; and 3) coordination and monitoring the progress of project implementation

Constituent LGUs with high incidence and magnitude of poverty, high prevalence of wasting, most vulnerable to shocks and disasters, with GIDA and with IP communities will be prioritized for the three-year project implementation.

II.	Project Objectives

The over-all objective of the project is to establish and strengthen the integrated management of acute malnutrition within the provincial health system and in at least 80% of its constituent municipalities and cities to achieve the service target of at least 90% of SAM and 90% of MAM cases treated/rehabilitated.

Specific objectives:

1)	Capacitate 100% of provincial health and nutrition human resources and at least 80% of municipalities and cities are trained on the appropriate competencies to identify, treat and manage acute malnutrition both under routine health program and during emergencies

3)	Organize Inpatient Therapeutic Care (ITC), Outpatient Therapeutic Care (OTC), and targeted Supplementary Feeding (TSFP) for the treatment and management of SAM and MAM cases to ensure timely delivery of quality services both under routine health program and during emergencies

3)	Ensure the effective implementation of the mechanism, standards and procedures for the supply and logistics management (planning, procurement, storage, allocation, distribution and monitoring) to ensure that commodities are available at treatment point

4)	Establish a functional mechanism for coordinating and monitoring the progress of interventions and activities on the management of acute malnutrition both under routine health program and during emergencies while at the same time track achievement of the service target of least 90% of SAM and 90% of MAM cases treated/rehabilitate

5)	Ensure the regular and timely provision of technical support and supportive supervision to IMAM program managers and implementers

6)	Establish partnership with existing food plants for the utilization of complementary foods produced for non-availability of Ready-to-Use Supplementary Food (RUSF)

III.	Project Outputs

1)	Established/Strengthened the treatment and management of acute malnutrition within the provincial, municipality and city health system to facilitate achievement of service target of at least 90% of SAM and and 90% of MAM cases treated/rehabilitated

2)	100% of provincial health and nutrition workers and at least 80% of constituent municipalities and cities are trained on the appropriate competencies to identify, treat and manage acute malnutrition both under routine health program and during emergencies

3)	100% of SAM and MAM cases identified through active case finding

4)	Inpatient Therapeutic Care (ITC), Outpatient Therapeutic Care (OTC), and targeted Supplementary Feeding (TSFP) for the treatment and management of SAM and MAM cases organized for the timely delivery of quality services both under routine health program and during emergencies

5)	Prescribed RUTF, RUSF and other commodities are available at all times at treatment points through improved supply chain management

6)	A mechanism for coordinating and monitoring the implementation of the integrated management of acute malnutrition both under routine health program and during emergencies established and functional

7) 	Regular and timely technical support and supportive supervision provided to IMAM program managers and implementers

8)	Complementary foods produced by existing food plants utilized for non-availability of RUSF

IV.	Project Major Activities and Implementation Schedule

The implementation of the project consists of the major activities shown in Table 1 below.

Table 1. Major Activities and Timeframe

| # | Major Activities | Timeframe |
| --- | --- | --- |
| 1 | Conduct of consultative and regular meetings | Starting January 2020 up to 2022 |
| 2 | Conduct of orientation sessions among entities involved in project implementation | January 2020 up to 2022 |
| 3 | Planning for the trainings (selection of target LGUs and participants, W1Einvitation, securing funds, venue, trainors/facilitators, supplies and materials, etc) | March 2020 and annually up to 2022 |
| 4 | Conduct of training of trainers and cascade trainings to LGUs | April 2020 and annually up to 2022 |
| 5 | Organization of ITC, OTC and TSF | 2020 |
| 6 | Improve case finding by LGUs | 2020 to 2022 |
| 7 | Improvement of the supply chain management of SAM and MAM commodities to ensure availability at treatment points | 2020 to 2022 |
| 8 | Establish linkage and partnership with existing food plants for use of complementary foods | 2020 to 2022 |
| 9 | Review of severe malnutrition cases (validation of nutritional assessment, interview, referral, follow up nutritional assessment, counselling) | February 2020 and annually up to 2022 |
| 10 | Development, reproduction and dissemination of IMAM protocols, IEC materials, collaterals, etc. | 2020 to 2022 |
| 11 | Conduct of regular monitoring visits and provision of continuing supportive supervision | Regularly as scheduled starting 2020 up to 2022 |
| 12 | Conduct of annual implementation review end-of-project evaluation for adjustments, re-planning and scaling up | 2020 to 2022 |

IV.	Project Organization and Management

Project management will be led by the Provincial Health Office with support from the Provincial Nutrition Office and in close coordination with Department of Health and the National Nutrition Council (as lead and co-lead of the National Program Management Team).  The PHO shall ensure that project management is done in partnership with development partners, NGOs, sectoral agencies, LGUs, and the existing delivery network.   The implementation of the project shall follow the protocols stipulated in the National Guidelines/Master Plan of Operations on the Management of Severe and Moderate Acute Malnutrition.

The Provincial Nutrition Committee which also acts as the Provincial Nutrition Cluster remains to be the IMAM coordinating structure that shall oversee the province-wide implementation of IMAM. The Provincial Health Office shall report to the Provincial Nutrition Committee the status of project implementation and important lessons that can guide the planning and implementation for the coming year.

V.	Estimates of Budgetary Requirements

The total estimated cost requirements of the project for the three-year implementation (2020-2022) amounts to P _______ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| # | Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2020 | 2021 | 2022 |  |
| 1 | Conduct of consultative and regular meetings | PHO, MHO |  |  |  |  |
| 2 | Conduct of orientation sessions among entities involved in project implementation |  |  |  |  |  |
| 3 | Planning for the trainings (selection of target LGUs and participants, invitation, securing venue, trainors/facilitators, supplies and materials, etc) |  |  |  |  |  |
| 4 | Conduct of training of trainers and cascade trainings to LGUs |  |  |  |  |  |
| 5 | Organization of ITC, OTC and TSF |  |  |  |  |  |
| 6 | Improve case finding by LGUs | DOH, PHO |  |  |  |  |
| 7 | Improvement of the supply chain management of SAM and MAM commodities to ensure availability at treatment points | PHO |  |  |  |  |
| 8 | Establish linkage and partnership with existing food plants for use of complementary foods | PHO, DOH |  |  |  |  |
| 9 | Review of severe malnutrition cases (validation of nutritional assessment, interview, referral, follow up nutritional assessment, counselling) | PHO, MHO |  |  |  |  |
| 10 | Development, reproduction and dissemination of IMAM protocols, IEC materials, collaterals, etc. | PHO, MHO |  |  |  |  |
| 11 | Conduct of regular monitoring visits and provision of continuing supportive supervision | PHO |  |  |  |  |
| 12 | Conduct of annual implementation review end-of-project evaluation for adjustments, re-planning and scaling up | PHO |  |  |  |  |

Assessment criteria in determining magnitude and severity of: wasting: <2.5% -  very low, 2.5% to < 5%-  low, 5% to < 10% - medium, 10% to <15% - High,  ≥15%  - Very High  (WHO 2018)

These are provided for in the National Guidelines on the Management of Severe Acute Malnutrition (SAM) for Under-Five Children and the National Guidelines on the Management of Moderate Acute Malnutrition (MAM) for Under-Five Children

The review of severe malnutrition cases shall be undertaken in compliance to the protocols set by DOH

Provides the overall direction and policy support in the implementation of the PIMAM program.