PROJECT BRIEF (PPA)

Project Title			: 	First 1000 Days Program

Location			:	Municipal/City-wide

Implementing Agency		:	Municipal/City Health Office

Start Date and Duration	: 	Jan 2020 to December 2022

Program Cost			:	P

___________________________________________________________________________________

I.	Rationale

The Philippines recognizes the alarming state of malnutrition in the country.  The 2015 Updating of the National Nutrition Survey revealed that stunting stood at 33.4% affecting 4.6 million under-five years old; wasting among the same age group was estimated at 7.1% equivalent to about 1 million children while overweight and obesity for children was reported to be about 3.8% equivalent to 0.5 million children under-five years old. In recognition of this alarming state of malnutrition, national plans and legislations such as the Philippine Development Plan, Philippine Plan of Action for Nutrition including its 17 Regional Plans of Action for Nutrition, Republic Act 11148: “Kalusugan at Nutrisyon ng Mag-Nanay Act” and Republic Act 11223: “Kalusugan Pangkalahatan (KP) Act” declare as a national policy the importance of investing in nutrition and the need for all sectors at all levels and local governments to work together in addressing all forms of malnutrition in the country, particularly stunting during the first 1,000 days of life.

The first 1,000 days of life refer to the period of pregnancy (270 days) which starts from conception up to the first two years of a child’s life (730 days).  This is the period during which key health, nutrition, early education and related services should be delivered to prevent stunting and ensure the optimum physical and mental development of the child. At the minimum, the reduction of stunting by 20 percent requires the implementation of six critical interventions at 90% coverage. These six critical interventions during the first 1000 days are as follows:

Figure 1. Six critical interventions in the First 1000 Days of life (Bhutta, 2013)

The first 1,000 days is also the period during which poor nutrition can have irreversible effects on the physical and mental development of the child, consequences of which are felt way into adulthood. Studies show a 40% reduction in the brain mass of a stunted child compared to their non-stunted counterparts. This reduction takes place in the temporal lobe, the part of the brain which is responsible for perception, comprehension, memory, and language. This negative impact on the brain takes a toll on the child’s ability to learn in school and consequently has an effect later in life.

Figure 2. Effect of stunting to the brain of a child compared to non-stunted counterparts and the temporal lobe, the affected part of the brain

The cost of malnutrition is high in terms of child mortality and losses to economy and productivity. About 45 percent of under-five mortality is attributable to malnutrition and estimates of the cost of maintaining the current level of program coverage and the current nutritional state is estimated at USD 4.5 billion annually.  In addition, global evidences show that compared to stunted children, children who get the right nutrition in their first 1,000 days:

Figure 3. Positive impact of proper nutrition in the first 1000 days to the

overall health and development of a child

To ensure achievement of planned outcomes the Philippine Plan of Action for Nutrition (PPAN) 2017-2022 identified focus provinces which have the highest prevalence of stunting of children under five years old to be prioritized for nutrition program management. Based on the same survey, the stunting rate of Zamboanga del Norte is at 41.4%. This is significantly higher than the national and regional averages (38%) affecting estimated 56,526 children under-five years old.  Zamboanga del Norte tops the provinces in Zamboanga Peninsula with the highest stunting prevalence.  This lists Zamboanga del Norte as one of the PPAN focus provinces.  As a municipality/city of the province, ___________ also mirrors the nutrition situation and will contribute to the overall progress of the province in achieving nutrition outcomes.

Addressing stunting during the first 1,000 days period in the municipality/city will have significant positive impact on health, education, improved human capital, and increased economic productivity.  The establishment of the municipality/city -wide program on F1K calls for the promotion of infant and young child feeding as well as provision of nutrition assistance in the form of dietary supplementation aimed at filling in the nutritional deficits or the gaps in food intake particularly of nutritionally-at-risk pregnant women and children 6-23 months belonging to food insecure households.  As a program, it will include interventions to improve the practice of exclusive breastfeeding and complementary feeding with continued breastfeeding by building and sustaining an enabling supportive environment in the LGU.

This municipal/city F1K program forms part of an overall province-wide program on the First 1000 Days where complementary activities such as mobile laboratory services, support through fund augmentation in enabling programs and dietary supplementation, coordination meetings, and other support services in the F1K.

These necessitate the development and implementation of a municipality/city-wide program focused on the first 1000 days of life that will ensure the availability and provision of key health, nutrition, early learning, and social development interventions for the optimum growth and development of the children of the Municipality/City of ______________.

II.	Project Objective

The project aims to establish the First 1,000 days program in the municipality/city implementing all six critical interventions including: 1) at least four pre-natal visits starting from the first trimester of pregnancy, 2) 180 tablets iron-folic acid supplementation, 3) balanced protein-energy dietary supplementation for pregnant women, 4) exclusive breastfeeding for children 0-6 months old, 5) age-appropriate complementary feeding, and 6) micronutrient supplementation (Vitamin A supplements and micronutrient powder), covering 90 % of the target pregnant and children in their first 24 months. Other supporting actions and services could form part of the project.

III. Key Sub-Outcome and Outputs

The project aims to prevent new cases of stunting thereby reducing the prevalence of stunting in the city/municipality.

The project will have the following outputs:

- Organization for the management of the F1K project in the municipality/city

- A Manual of Operations for the program developed, outlining the entire project system and process covering the responsibilities of the various agencies involved in the project, selection of first cohort of women to be enrolled in the project and monitored, the supply chain, the reporting and monitoring system, the process for barangay operation of F1K, operation of the F1K mobile laboratory for the pregnant women, the review of the health system compliance of the relevant six interventions for F1K, and other aspects and the financing of the project.

- Mobilized barangays and agency stakeholders in the F1K project.

- Project strategy selected by the municipality/city to achieve the outcomes the project hopes to achieve.

- First year review completed with adjustments on strategy to address bottlenecks and issues

- First report of progress and intermediate outcomes

- Second year report on progress and intermediate outcomes

- Expanded coverage of the project to the entire municipality/city

IV. Major Activities

- Learning visit to Quezon Province to draw lessons from Q1K program implementation Mobilization of the municipality/city agencies and structures to establish the F1K project

- Formal assignment of responsibilities of the project by LGU

- Issuance and implementation of an enabling policy supporting the establishment of the First 1000 Days program and securing program budget by through extensive social preparation activities including advocacy/Interface with the LCEs, members of the Sangguniang Bayan, local nutrition committees to secure political support for the program.

- Production of the manual of operations of the F1K program by key officers responsible for the project.

- Training/capacity building for all those to be involved in the program. A defined Program Organization and Management system including the designation/hiring of focal persons and F1K coordinators to strengthen coordination, monitoring and assessment of F1K to ensure immediate remedial measures are carried out, including program stakeholders made to understand the program’s objectives with respective roles in the program defined in preparation for program implementation

- Undertake a review of compliance to F1K standards, specifically in six critical interventions, involving all RHUs and integrate the results of such study in successive plans of RHUs, barangays, and other agencies involved in the First 1000 Days

- Establish baseline data for the pilot the implementation of the program in select barangays and develop and utilize a harmonized information management system for the efficient and effective implementation of F1K

- Provide budget allocation for the selected strategy for delivery for organized dietary supplementation for nutritionally at risk pregnant women and children 6-23 months old belonging to food insecure households through the provision of sufficient and quality supplementary food to maintain their normal nutritional status and prevent low birth weight and stunting using the various options/modes available for the LGU.

- Mobilize/strengthen partnership with NGOs, development partners, private sector and other community organizations (4Ps beneficiaries, Rural Improvement Clubs, etc.) for the effective implementation and sustainability of the project.

- Implementation of the F1K project

- Periodic monitoring of progress and management adjustments

- First year Program Implementation Review and planning of second year and third year implementation including adjustments in the AIP

IV.	Implementation Schedule

The Municipal/City Nutrition Committee can draw lessons and inspiration from the Province of Quezon Q1K implementation and shall use these as building blocks for the establishment of the F1K program.  Other interrelated and reinforcing activities are outlined in the Schedule of Activities (Gantt chart) in Annex A of this proposal.

V.	Project Organization and Management

Project management will be led by the Municipal/City Health Office with support from the Municipal/City Nutrition Office and in partnership with critical stakeholders including sectoral agencies, NGOs, academe, development partners and the constituent barangays.

The Municipal/City Nutrition Committee (M/CNC) shall provide overall policy support to the program.  The M/CNC shall/may organize an F1K Program Technical Working Group composed of representatives from the M/CHO, M/CNO, MSWDO, Municipal/City DILG, among others and shall provide the needed technical support.  It shall develop tools and guidelines, prepare reports, and conduct monitoring visits.

At the local level, city/municipal/barangay nutrition committees shall continue to provide the mechanism for coordinating the F1K Program. The Municipal/City Nutrition Action Officer shall be considered as the F1K Program focal persons unless the Mayor opt to hire a full time F1K Program Coordinator. F1K coordinators at barangay levels will be assigned/deployed to oversee the implementation of F1K activities and ensure that beneficiaries receive quality services.

VI.	Estimates of Budgetary Requirements

The establishment of the F1K program will require an estimated budget of P _________ for the first three years of implementation.  This is broken down by activity and by year as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| # | Major Activity | Agency/ies Responsible | Budgetary Requirements |  |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2020 | 2021 | 2022 |  |  |
| 1 | Learning visit to Quezon Province to draw lessons from Q1K program implementation | M/CHO, Brgys |  |  |  |  |  |
| 2 | Mobilization of the municipality/city agencies and structures to establish the F1K project | M/CHO, Brgys |  |  |  |  |  |
| 3 | Production of the manual of operations of the F1K project by key officers responsible for the project. | M/CHO |  |  |  |  |  |
| 4 | Training/capacity building for all those to be involved in the program under a defined Program Organization and Management system | M/CNO |  |  |  |  |  |
| 5 | Designation/hiring of focal persons and F1K coordinators at the municipality/city down to the barangay level to strengthen coordination, monitoring and assessment of F1K to ensure immediate remedial measures are carried out | Office of the Mun/City Mayor |  |  |  |  |  |
| 6 | Review of compliance to F1K standards, specifically in six critical interventions, involving all RHUs and integrate the results of such study in successive plans of RHUs, barangays, and other agencies involved in the First 1000 Days | Office of the Mun/City Mayor |  |  |  |  |  |
| 7 | Mobilize partnership with NGOs, development partners, private sector and other community organizations (4Ps beneficiaries, Rural Improvement Clubs, etc.) for the effective implementation and sustainability of the project. |  |  |  |  |  |  |
| 8 | Establish baseline data for the pilot the implementation of the program in select barangays and develop and utilize a harmonized information management system for the efficient and effective implementation of F1K | M/CHO, M/CNO, Brgys |  |  |  |  |  |
| 9 | Ensure that the municipality/city and all constituent barangays have budget allocation and are implementing organized dietary supplementation for nutritionally at risk pregnant women and children 6-23 months old using the various options/modes available for the LGU | M/CHO, Brgys |  |  |  |  |  |
| 10 | Full implementation of the F1K program | M/CNO |  |  |  |  |  |
| 11 | Periodic monitoring of progress and management adjustments | M/CNO |  |  |  |  |  |
| 12 | First year Program Implementation Review and planning of second year and third year implementation including adjustments in the AIP | M/CHO and concerned departments |  |  |  |  |  |

Annex 1. Major Activities and Timeframe for the First 1000 Days Program

|  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Major Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |
| 1 | Learning visit to Quezon Province to draw lessons from Q1K program implementation Mobilization of the municipality/city agencies and structures to establish the F1K program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Formal assignment of responsibilities of the project by the LGU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Issuance and implementation of an enabling policy supporting the establishment of the First 1000 Days program and securing program budget by through extensive social preparation activities including advocacy/Interface with the LCEs, members of the Sangguniang Bayan, local nutrition committees to secure political support for the program. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Production of the manual of operations of the F1K project by key officers responsible for the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Training/capacity building for all those to be involved in the program. A defined Program Organization and Management system including the designation/hiring of focal persons and F1K coordinators to strengthen coordination, monitoring and assessment of F1K to ensure immediate remedial measures are carried out, including program stakeholders made to understand the program’s objectives with respective roles in the program defined in preparation for program implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Undertake a review of compliance to F1K standards, specifically in six critical interventions, involving all RHUs and integrate the results of such study in successive plans of RHUs, barangays, and other agencies involved in the First 1000 Days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Establish baseline data for the pilot the implementation of the program in select barangays and develop and utilize a harmonized information management system for the efficient and effective implementation of F1K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Ensure that the municipality/city and all constituent barangays have budget allocation and are implementing organized dietary supplementation for nutritionally at risk pregnant women and children 6-23 months old belonging to food insecure households through the provision of sufficient and quality supplementary food to maintain their normal nutritional status and prevent low birth weight and stunting using the various options/modes available for the LGU. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Strengthen partnership with NGOs, development partners, private sector and other community organizations (4Ps beneficiaries, Rural Improvement Clubs, etc.) for the effective implementation and sustainability of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Full implementation of the F1K project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | Periodic monitoring of progress and management adjustments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | First year Program Implementation Review and planning of second year and third year implementation including adjustments in the AIP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

The six critical interventions are; 1) four pre-natal visits starting from the first trimester of pregnancy, 180 tables iron-folic acid supplementation, 3) balanced protein-energy dietary supplementation for pregnant women, 4) exclusive breastfeeding for children 0-6 months old, 5) age-appropriate complementary feeding, and 6) micronutrient supplementation in the form of Vitamin A and Micronutrient Powder (MNP)