PROJECT BRIEF #11

| Project Title: | Production support services (distribution of planting materials and vegetable seeds) |
| --- | --- |
| Project Location: | Municipality/City-wide, farming communities |
| Proponent: | Municipality/City |
| Implementing Agency: | Department of Agriculture Field Office with Municipality/City Agriculture Office Municipality/City Nutrition Office |
| Start Date and Duration: | January 2020 to December 2022. |
| Beneficiaries: | Farmers belonging to food insecure and nutritionally vulnerable families |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

Provision of agricultural support services to farming households is a regular undertaking of the local government unit together with the Department of Agriculture Regional Field Office and is one of the identified development projects that can be tweaked to become nutrition-sensitive. The agricultural inputs provided assist the farmers during crop seasons and provide them with additional resources for increased farm productivity. Such service can be further tweaked to become a comprehensive nutrition-sensitive project that mobilizes all farming families within the municipality/city to establish home vegetable gardens – the Gulayan – to produce for their daily fruit and vegetable needs in a sustainable manner through the support of an LGU-established central garden – Sentrong Gulayan – that regularly supplies constituent barangays with nutritionally-relevant, climate-resilient, and indigenous seed varieties.

The established Sentrong Gulayan aims to improve the sustainability and productivity of home and community gardens which hold a vital role in facilitating the achievement of nutritional objectives. The central garden aims to do this by decentralizing seed preservation and propagation of diverse indigenous fruits, vegetables and root crops, demonstrating climate-smart and nutrition-smart agriculture through bio-intensive gardening, and training constituent barangays to adopt the strategy for the eventual improvement of agricultural and nutritional outcomes, especially among food insecure and nutritionally-vulnerable households. The Sentrong Gulayan will also be an augmenting source of inputs for feeding centers, with surplus linked to markets and private sector buyers.

There is an estimated number of ___ farming families in the Municipality/City of __________ considered as among the poorest sector of the community who are expected to benefit from the project. These poor families are the most vulnerable to health and nutrition issues, especially women and children. Malnutrition has significant negative consequences particularly in terms of poor health, lost human capital, and decreased economic productivity. Such negative effects of malnutrition can be prevented among members of poor families by enabling access to food through interventions such as the nutrition-sensitive production support service in the municipality/city. The project will be harnessed to lead towards the establishment of a LGU-wide movement on home and community production that originates from a central garden, and the enhancing of knowledge, skills, and practices on proper nutrition, for improved food security and overall nutritional status in the municipality/city.

- Project Objectives

In the Production Support Services in the Municipality/City of _____________, incorporate nutritional considerations through the prioritization of beneficiaries from food insecure and nutritionally vulnerable households who will receive agricultural inputs and training, which together with provision of nutrition education, enhance their knowledge, skills, and practices on proper nutrition, and facilitate the improvement of food security and nutritional status of children in the beneficiary households. The inputs provided to the farmers, such as seeds and other planting materials, will be coming from the central garden established by the LGU.

- Project Output

- All Production Support Services in the municipality/city apply nutritional considerations by selecting beneficiary households who are identified as food insecure and nutritionally-vulnerable

- A municipality/city central garden established to provide for the initial and sustained seed requirements of the beneficiaries, serve as hub for the preservation of nutritionally-relevant, climate-hardy, and indigenous crop varieties, and showcase models for sustainable home food production

- At least 80% of the barangays within the municipality/city provided with assistance and have an operational community food garden acting as source of fruits and vegetables for feeding centers in the community, source of income for the barangay, and an augmenting source of vegetables for households with limited space for home gardening.

- At least 85% of beneficiaries who received training on Bio-intensive Gardening (BIG) and inputs for home food production have established a fully functional sustainable home garden for increased food security and improved nutritional status

- A value chain established for the surplus fruits and vegetables produce of the home food gardens involving markets, feeding centers, complementary food plants, and other organized systems of selling of the municipality/city

- A system to ensure adequate nutrition education and mentoring of all families involved in the nutrition-sensitive production support services is established and fully operational resulting in effective coaching and mentoring on maternal and infant and young child nutrition and proper meal management within households

- The municipality/city have issued local policies institutionalizing production support services and other related nutrition-sensitive projects.

- Project Major Activities and Implementation Schedule

The project consists of five major activities that is implemented sequentially as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Conduct of consultative meetings with DA FO, M/CPDO, M/CAO, M/CNO, and other relevant stakeholders for the implementation of the project | August 2019 |
| 2 | Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | September 2019 |
| 3 | Conduct of training and training related events for farms such as technology transfer, schools-on-the-air, farmers field day, sustainable agriculture practices, palay check, bio-intensive gardening, and other social mobilizations | September 2019, monthly |
| 4 | Implementation of the project | October 2019 |
| 5 | Monitoring, reporting, evaluation, and scaling up | Quarterly from December 2019 |

- Project Management and Organization

This project is led by the Municipality/City Planning and Development Office with support from the Municipality/City Agriculture Office and the Department of Agriculture Regional Field Office. The Municipal/City Nutrition Office and the Local Nutrition Committees will take the lead in identifying the project beneficiaries, support in follow-up, and assist in project monitoring. Project implementation status, issues, and concerns will be discussed in the Local Nutrition Committees for remedial actions.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| Conduct of consultative meetings with DA FO, M/CAO, M/CNO, and other relevant stakeholders for the implementation of the project | DA FO M/CPDO M/CAO M/CNO |  |  |  |  |
| Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | M/CNO |  |  |  |  |
| Conduct of training and training related events for farms such as technology transfer, schools-on-the-air, farmers field day, sustainable agriculture practices, palay check, bio-intensive gardening, and other social mobilizations | DA FO M/CAO M/CNO |  |  |  |  |
| Implementation of the project | M/CAO M/CNO |  |  |  |  |
| Monitoring, reporting, evaluation, and scaling up | M/CPDO M/CAO M/CNO |  |  |  |  |