# PROJECT BRIEF #2

| Project Title: | Targeted Actions to Reduce Poverty and Generate Economic Transformation (TARGET) |
| --- | --- |
| Project Location: | Municipal/City-wide, fishing communities |
| Proponent: | Municipality/City |
| Implementing Agency: | BFAR Regional Office Municipality/City Nutrition Office |
| Start Date and Duration: | January 2020 to December 2022. |
| Beneficiaries: | Fisherfolks belonging to food insecure and nutritionally vulnerable families |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

One of the projects under the nutrition-sensitive program is the Targeted Actions to Reduce Poverty and Generate Economic Transformation (TARGET), a project under the Bureau of Fisheries and Aquatic Resources of the Department of Agriculture (BFAR – DA) designed to reduce poverty in fishing communities through the provision of comprehensive livelihood packages which include skills training on resource management and protection. Such project is tweaked to become nutrition-sensitive by prioritizing assistance to food insecure and nutritionally-vulnerable households, providing them with adequate nutrition education, thereby facilitating improvement in food security and nutritional status within beneficiary households.

To facilitate the implementation of TARGET in the LGU, BFAR deploys Fishery Livelihood Development Technicians (FLDTs) in coastal municipalities with high concentration of fisherfolk and highest incidence of poverty who are at the same time the most food insecure and nutritionally vulnerable. The FLDTs will be working together with the Barangay Nutrition Scholars in ensuring that there is adequate nutrition education and mentoring of all families involved in the project.

Fisherfolk communities are one of the poorest sectors of the country. There is an estimated number of ___ fisherfolk families in the Municipality/City of ________ considered as among the poorest sector of the community who are to benefit from the various interventions provided by TARGET such as livelihood assistance, sustainable resource management, provision of Community Fish Landing Center (CFLCs), smokehouse, seaweed/fish driers and other supportive facilities, as well as marketing assistance. Such forms of assistance shall be provided to beneficiary communities to secure increases in income among the identified food insecure and nutritionally-vulnerable households, providing them with an improved capacity to buy food of sufficient quality and quantity, which along with the received nutrition education, would secure the overall improvement of nutritional status in the municipality/city.

- Project Objectives

In all TARGET project areas in the Municipality/City of __________, incorporate nutritional considerations through the inclusion of beneficiaries from food insecure and nutritionally vulnerable households in fishing communities who will receive comprehensive livelihood packages that provide for increased income, which together with the provision of nutrition education, enhance their knowledge, skills, and practices on proper nutrition, and facilitate the improvement of food security and nutritional status of the children in the beneficiary households.

- Project Outputs

- All TARGET project areas in the municipality/city apply nutritional considerations by selecting beneficiary households who are identified as food insecure and nutritionally-vulnerable

- A system to ensure adequate nutrition education and mentoring of all families involved in the nutrition-sensitive TARGET project in the municipality/city is established and fully operational resulting in effective coaching and mentoring on maternal and infant and young child nutrition and proper meal management within households

- At least 85% of the TARGET household beneficiaries have enhanced knowledge, skills, and practices on maternal and infant and young child nutrition, and have improved levels of food security and nutritional status of children from such households

- The municipality/city have issued local policies institutionalizing nutrition-sensitive TARGET project and other related nutrition-sensitive projects

- Project Major Activities and Implementation Schedule

The project consists of five major activities that are implemented sequentially as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Consultative meetings and forging of agreements between BFAR RO and the M/CNO, site assessment and validation | January 2020 |
| 2 | Selection/Identification and of target families and recruitment of workers belonging to food insecure and nutritionally disadvantaged families | January 2020 |
| 3 | Implementation of the project | February 2020 |
| 4 | Nutrition education to beneficiaries, follow-up, and monitoring by BNS | February 2020, regularly conducted to 2022 |
| 5 | First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | June 2020 onwards to 2020 |

- Project Management and Organization

This project is led by the BFAR Regional Office. The Municipal/City Nutrition Office and the Local Nutrition Committees will take the lead in identifying the project beneficiaries, support in follow-up, and assist in project monitoring. Project implementation status, issues, and concerns will be discussed in the Local Nutrition Committees for remedial actions.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

Table 3. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| Consultative meetings and forging of agreements between BFAR RO and the M/CNO, site assessment and validation | BFAR-RO C/MNO |  |  |  |  |
| Selection/Identification and of target families and recruitment of workers belonging to food insecure and nutritionally disadvantaged families | C/MNO |  |  |  |  |
| Implementation of the project | BFAR-RO, C/MNO |  |  |  |  |
| Nutrition education to beneficiaries, follow-up, and monitoring by BNS | C/MNO |  |  |  |  |
| First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | BFAR-RO C/MNO |  |  |  |  |