# PROJECT BRIEF #3

| Project Title: | Project ConVERGE (Convergence on Value Chain Enhancement for Rural Growth and Empowerment) |
| --- | --- |
| Project Location: | Municipality/City-wide, farming communities |
| Proponent: | Municipality/City |
| Implementing Agency: | Department of Agrarian Reform Regional Office (DAR RO) Municipality/City Nutrition Office |
| Start Date and Duration: | January 2020 to December 2022. |
| Beneficiaries: | Disadvantaged, food insecure, and nutritionally vulnerable families in agrarian reform communities (ARCs) |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

One of the projects identified under the nutrition-sensitive program is the Convergence on Value Chain Enhancement for Rural Growth and Empowerment (Project ConVERGE), an agribusiness development project by the Department of Agrarian Reform that aims to help rural farmers by increasing their capacity for increased income through the provision of trainings on various entrepreneurial undertakings for their crop harvests. In tweaking Project ConVERGE to become nutrition-sensitive, priority shall be given to food insecure and nutritionally-vulnerable households within Agrarian Reform Communities (ARCs) providing them with adequate nutrition education, facilitating improvement in food security and nutritional status of beneficiary households.

There is an estimated number of ___ agrarian reform beneficiaries from agrarian reform communities (ARCs) in the Municipality/City of __________ considered as one of the poorest sectors of the community who are to benefit from the trainings provided by the nutrition-sensitive Project ConVERGE. Such forms of assistance in agricultural enterprise development shall be provided to beneficiary communities to secure increases in income among the identified food insecure and nutritionally-vulnerable households, providing them with an improved capacity to buy food of sufficient nutritional quality and quantity, which along with the received nutrition education, would secure the overall improvement of nutritional status of pregnant and lactating women, and children in the municipality/city.

- Project Objective

In all Project ConVERGE projects in the Municipality/City of __________, incorporate nutritional considerations through the inclusion of beneficiaries from food insecure and nutritionally vulnerable households within agrarian reform communities (ARCs) who will receive livelihood trainings and assistance that provide for increased income, which together with provision of nutrition education, enhance their knowledge, skills, and practices on proper nutrition, and facilitate the improvement of food security and nutritional status of children in the beneficiary households.

- Project Outputs

- All Project ConVERGE interventions in the municipality/city apply nutritional considerations by selecting beneficiary households within agrarian reform communities (ARC) who are identified as food insecure and nutritionally-vulnerable

- A system to ensure adequate nutrition education and mentoring of the families involved in the nutrition-sensitive Project ConVERGE in the municipality/city is established and fully operational resulting in effective coaching and mentoring on maternal and infant and young child nutrition and proper meal management within households

- At least 85% of the Project ConVERGE beneficiaries have enhanced knowledge, skills, and practices on maternal and infant and young child nutrition, and have improved levels of food security and nutritional status of children of these households

- The municipality/city have issued local policies institutionalizing nutrition-sensitive Project ConVERGE and other related nutrition-sensitive projects.

- Project Major Activities and Implementation Schedule

The project consists of five major activities that are implemented sequentially as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Consultative meetings and forging of agreements between DAR, C/MNO, and other relevant stakeholders of the project | January 2020 |
| 2 | Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | January 2020 |
| 3 | Implementation of the project | February 2020 |
| 4 | Nutrition education to beneficiaries, follow-up, and monitoring by BNS | February 2020, regularly conducted to 2022 |
| 5 | First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | June 2020 onwards to 2020 |

- Project Management and Organization

This project is led by the Department of Agrarian Reform Regional Office with the Municipal/City Nutrition Office who will take the lead in identifying the project beneficiaries, provide support in follow-up, and assist in project monitoring. Project implementation status, issues, and concerns will be discussed in the Local Nutrition Committees for remedial actions.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| Consultative meetings and forging of agreements between DAR, C/MNO, and other relevant stakeholders of the project | DAR RO, C/MAO, C/MNO |  |  |  |  |
| Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | C/MNO |  |  |  |  |
| Implementation of the project | DAR RO, C/MAO, C/MNO |  |  |  |  |
| Nutrition education to beneficiaries, follow-up, and monitoring by BNS | C/MNO |  |  |  |  |
| First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | DAR RO, C/MAO, C/MNO |  |  |  |  |