# PROJECT BRIEF #4

| Project Title: | Special Area for Agricultural Development (SAAD) |
| --- | --- |
| Project Location: | Municipality/City-wide, farming communities |
| Proponent: | Municipality/City |
| Implementing Agency: | Department of Agriculture Regional Field Office (DA RFO) Municipality/City Nutrition Office |
| Start Date and Duration: | January 2020 to December 2022. |
| Beneficiaries: | Disadvantaged, food insecure, and nutritionally vulnerable farming families |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

One of the projects identified under the nutrition-sensitive program is the Special Area for Agricultural Development (SAAD), a project of the Department of Agriculture designed to help alleviate poverty among the marginalized sectors on agriculture and fisheries through the provision of livelihood interventions and agricultural inputs for increased farm productivity. In tweaking SAAD to become nutrition-sensitive, priority shall be given to food insecure and nutritionally-vulnerable households within Agrarian Reform Communities (ARCs) who will also receive adequate nutrition education to ensure that the increase in income is translated to improved practices on nutrition, which along with the improved socio-economic condition and access to food, would yield to the overall improvement of nutritional status of children from such households.

There is an estimated number of ___ families in the agricultural sector and _____ families in the fishing sector in the Municipality/City of ___________ considered as among the poorest sector of the community who are expected to benefit from the nutrition-sensitive SAAD project, specifically from its two major component activities – (1) Social Preparation which will encompass the series of training (including needs assessments) to ensure readiness and empowerment of the SAAD beneficiaries in accepting and managing the interventions being provided by the program and (2) Livelihood Interventions which provides livelihood projects based on the assessed needs of the recipients.

Such forms of assistance shall be provided to beneficiary households through the nutrition-sensitive SAAD project to secure increases in income among the identified food insecure and nutritionally-vulnerable households, providing them with an improved capacity to buy food of sufficient quality and quantity, which along with the received nutrition education, would secure the overall improvement of nutritional status in the municipality/city.

- Project Objectives

In implementing the SAAD project in the Municipality/City of __________, incorporate nutritional considerations through the inclusion of beneficiaries from food insecure and nutritionally vulnerable households in farming and fishing communities who will receive livelihood inputs and trainings that provide for increased income, which together with provision of nutrition education, will enhance their knowledge, skills, and practices on proper nutrition, and facilitate the improvement of food security and nutritional status of the children in the beneficiary households.

- Project Outputs

- All SAAD project areas in the municipality/city apply nutritional considerations by selecting beneficiary households who are identified as food insecure and nutritionally-vulnerable

- A system to ensure adequate nutrition education and mentoring of the families involved in the nutrition-sensitive SAAD project in the municipality/city is established and fully operational resulting in effective coaching and mentoring on maternal and infant and young child nutrition and proper meal management within households

- At least 85% of the SAAD household beneficiaries have enhanced knowledge, skills, and practices on maternal and infant and young child nutrition, and have improved levels of food security and nutritional status of children of these households

- The municipality/city have issued local policies institutionalizing nutrition-sensitive SAAD project and other related nutrition-sensitive projects.

- Project Major Activities and Implementation Schedule

The project consists of five major activities that are implemented sequentially as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Consultative meetings and forging of agreements between DA RFO and the M/CNO, site assessment and validation | January 2020 |
| 2 | Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | January 2020 |
| 3 | Implementation of the project | February 2020 |
| 4 | Nutrition education to beneficiaries, follow-up, and monitoring by BNS | February 2020, regularly conducted to 2022 |
| 5 | First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | March 2020 onwards to 2020 |

- Project Management and Organization

This project is led by the DA Regional Field Office. The Municipal/City Nutrition Office and the Local Nutrition Committees will take the lead in identifying the project beneficiaries, support in follow-up, and assist in project monitoring. Project implementation status, issues, and concerns will be discussed in the Local Nutrition Committees for remedial actions.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| Consultative meetings and forging of agreements between DA RFO and the M/CNO, site assessment and validation | DA-RFO, M/CAO, C/MNO |  |  |  |  |
| Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | C/MNO |  |  |  |  |
| Implementation of the project | DA-RFO M/CAO |  |  |  |  |
| Nutrition education to beneficiaries, follow-up, and monitoring by BNS | C/MNO |  |  |  |  |
| First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | DA-RFO C/MAO C/MNO |  |  |  |  |