# PROJECT BRIEF #5

| Project Title: | Sustainable Livelihood Program |
| --- | --- |
| Project Location: | Municipality/City-wide |
| Proponent: | Municipality/City |
| Implementing Agency: | Department of Social Welfare and Development Field Office (DSWD FO) Municipality/City Nutrition Office |
| Start Date and Duration: | January 2020 to December 2022 |
| Beneficiaries: | Disadvantaged, food insecure, and nutritionally vulnerable households |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

One of the projects identified under the nutrition-sensitive program is the Sustainable Livelihood Program (SLP), a community-based capacity-building program by the Department of Social Welfare and Development (DSWD) which aims to improve the socio-economic status of its participants in its two-track programs: Employment Facilitation Track and Microenterprise Development Track. In tweaking SLP to become nutrition-sensitive, priority for interventions shall be given to food insecure and nutritionally-vulnerable households who will also be receiving adequate nutrition education to ensure that the increase in income is translated to improved practices on nutrition, which along with the improved socio-economic condition and access to food, would yield the improvement of nutritional status of children from such households.

According to the latest data, poverty incidence in the Municipality/City of ________ stands at ___%, totaling to an estimated number of ___ households/families who are to benefit from the interventions of the SLP. Beneficiaries will gain access to employment opportunities through the Employment Facilitation Track and/or receive assistance on establishing entrepreneurial undertakings through the Microenterprise Development Track. Both tracks are seen to ultimately provide a sustainable income source to the food insecure and nutritionally-vulnerable households. The SLP is implemented through the Community-Driven Enterprise Development Approach which equips program participants to actively contribute to production and labor markets by looking at available resources and accessible markets.

Such forms of assistance provided by the nutrition-sensitive SLP shall be provided to beneficiary households to secure increases in income among the identified food insecure and nutritionally-vulnerable households, providing them with an improved capacity to buy food of sufficient nutritional quality and quantity, which along with the received nutrition education, would secure the overall improvement of nutritional status of pregnant and lactating women, infants and children in the municipality/city.

- Project Objectives

In the Sustainable Livelihood Program in the Municipality/City of __________, incorporate nutritional considerations through the inclusion of beneficiaries from food insecure and nutritionally vulnerable households who will receive livelihood packages or employment facilitation that provide for increased income, which together with the provision of nutrition education will enhance their knowledge, skills, and practices on proper nutrition, and facilitate the improvement of food security and nutritional status of the children in the beneficiary households.

- Project Outputs

- The SLP in the municipality/city apply nutritional considerations by selecting beneficiaries coming from identified food insecure and nutritionally-vulnerable households

- A system to ensure adequate nutrition education and mentoring of all families involved in the nutrition-sensitive SLP in the municipality/city is established and fully operational resulting in effective coaching and mentoring on maternal and infant and young child nutrition and proper meal management within households

- At least 85% of the SLP beneficiaries have enhanced knowledge, skills, and practices on maternal and infant and young child nutrition, and have improved levels of food security and nutritional status of children of these households

- The municipality/city have issued local policies institutionalizing nutrition-sensitive SLP and other related nutrition-sensitive projects

- Project Major Activities and Implementation Schedule

The project consists of five major activities that are implemented sequentially as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Consultative meetings between DSWD FO, M/CSWDO, C/MNO, and other relevant stakeholders of the project | January 2020 |
| 2 | Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | January 2020 |
| 3 | Implementation of the project | February 2020 – March 2020 |
| 4 | Nutrition education to beneficiaries, follow-up, and monitoring by BNS | February 2020, regularly conducted to 2022 |
| 5 | Monitoring, assessment, and adjustments | March 2020 onwards |

- Project Management and Organization

This project is led by the Department of Social Welfare and Development Regional Office supported by Municipal/City Social Welfare and Development Office. The Municipal/City Nutrition Office and the Local Nutrition Committees will take the lead in identifying the project beneficiaries and assist in project monitoring. Project implementation status, issues, and concerns will be discussed in the Local Nutrition Committees for remedial actions.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| Consultative meetings between DSWD FO, M/CSWDO, C/MNO, and other relevant stakeholders of the project | DSWD FO, C/MSWDO, C/MNO |  |  |  |  |
| Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | C/MNO |  |  |  |  |
| Implementation of the project | DSWD FO |  |  |  |  |
| Nutrition education to beneficiaries, follow-up, and monitoring by BNS | C/MNO |  |  |  |  |
| First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | DSWD FO, C/MNO |  |  |  |  |