# Project #0

| Project Title: | Tweaking development projects of constituent LGUs to become nutrition-sensitive |
| --- | --- |
| Project Location: | Province-wide |
| Proponent: | Provincial Government of ______________ |
| Implementing Agency: | Provincial Planning and Development Office Provincial Nutrition Office |
| Start Date and Duration: | June 2020 to December 2022. |
| Beneficiaries: | Constituent municipality and city LGUs |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

In the Province of ______________, there are currently ___ identified development projects that hold potential for tweaking to become nutrition-sensitive and contribute to the achievement of nutritional outcomes. These projects are implemented by various local, regional, and national government agencies across the municipalities and cities of the province. Such projects are implemented to improve the economic situation of poor households to provide them with better living outcomes. A strategy for tweaking such projects is through the prioritization of food insecure and nutritionally vulnerable households, as well as provision of nutrition education to ensure that increases in income are translated into actual nutrition outcomes for the targeted household.

The role of the province in the implementation of such projects are in the form of setting programmatic direction for projects of the municipality and city. The province also would establish linkages and networks among other institutions to support the expansion and scaling of nutrition sensitive projects, in addition to the continuing social mobilization efforts. Release of policies supporting nutrition-sensitive projects will institutionalize and ensure the continuity of projects. Monitoring of the province through fully functional systems of monitoring will be done to ensure that the outcomes set by these nutrition-sensitive projects are achieved in each year of implementation.

It is incumbent upon the province to ensure that such development projects implemented in the municipality and city are tweaked to become nutrition sensitive. The Local Chief Executive, with support from the Provincial Nutrition Office, hold a critical role in convening the sectors, as well as constituent local government units so that each gear is moving towards the common goal of improving nutritional status among pregnant and lactating women, infants and children.

- Project Objectives

For period 2017 to 2022, in all constituent municipalities and cities of the Province of ______________,  implement the tweaking of development projects to become nutrition-sensitive, to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions.

- Project Outputs

- All constituent municipalities and cities of the Province of ___________, implement tweaking of their development projects to become nutrition-sensitive for the achievement of nutritional outcomes

- A fully functional reporting and review system is established in the province to monitor the results of the nutrition-sensitive projects implemented by various sectoral offices across all constituent municipalities and cities

- The provincial local government and its Governor, appreciate the value and results of implementing development projects with tweaking to become nutrition-sensitive, and predisposed to replicating such tweaking of projects in all municipalities and cities

- The provincial government has issued local policies institutionalizing the implementation of nutrition-sensitive projects within their respective Province

- Project Major Activities and Implementation Schedule

The project consists of four major activities as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Advocacy to LCE and sectoral offices of the province | January 2020 |
| 2 | Workshop on nutrition-sensitive tweaking for constituent LGUs | February 2020 |
| 3 | Information dissemination and technical assistance to constituent LGUs | February 2020, continuing to 2022 |
| 4 | Monitoring and evaluation, reporting and adjustments | July 2020, continuing to 2022 |
| 5 | Annual Project Implementation Review with constituent municipalities and cities | January 2020, Every first quarter of the year |

- Project Management and Organization

The project is led by the Provincial Nutrition Office who will conduct advocacy, monitoring, and evaluation. The PNO will be working with the Provincial Planning and Development Office who will provide support in advocacy and convening the constituent municipalities and cities. Other sectoral offices of the province will assist in the provision of technical assistance to LGUs in their nutrition-sensitive projects.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

|  | Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2020 | 2021 | 2022 |  |
| 1 | Advocacy to LCE and sectoral offices of the province | PPDO PNO |  |  |  |  |
| 2 | Workshop on nutrition-sensitive tweaking for constituent LGUs | PPDO PNO |  |  |  |  |
| 3 | Information dissemination and technical assistance to constituent LGUs | PNO, sectoral offices |  |  |  |  |
| 4 | Monitoring and evaluation, reporting and adjustments | PNO |  |  |  |  |
| 5 | Annual Project Implementation Review with constituent municipalities and cities | PPDO PNO |  |  |  |  |