# PROJECT BRIEF #10

| Project Title: | Village Level Farm Focused Enterprise Development (VLFED) |
| --- | --- |
| Project Location: | Province-wide, agrarian reform communities |
| Proponent: | Province |
| Implementing Agency: | Provincial Agrarian Reform Office with DAR RO Province Planning and Development Office Province Nutrition Office |
| Start Date and Duration: | June 2020 to December 2022. |
| Beneficiaries: | Agrarian reform beneficiaries identified as food insecure and nutritionally vulnerable |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

One of the projects under the nutrition-sensitive program is the Village Level Farm-focused Enterprise Development (VLFED), a project of the Department of Agrarian Reform (DAR) which aims to create additional livelihood opportunities for farmer beneficiaries within agrarian reform communities (ARCs) who have limited capital and do not have sufficient income. In tweaking VLFED to become nutrition-sensitive, priority beneficiaries shall be those food insecure and nutritionally-vulnerable households within Agrarian Reform Communities (ARCs) which along with livelihood trainings, will also be receiving adequate nutrition education.

There is an estimated number of ___ agrarian reform beneficiaries in the Province of ____________ considered as among the poorest sector of the community and are expected to benefit from the nutrition-sensitive VLFED. Targeted households will receive inputs to livelihood and other comprehensive livelihood packages and trainings aimed to increase income. Development interventions will focus on enhancing the level of appreciation of beneficiaries in establishing profitable rural enterprises that are anchored on their crop-based and area-specific production systems. The said crops and cultured commodities (including the resulting waste materials/farm debris) will be used as raw materials for value addition activities, the products of which are processed food and/or non-food products to be developed/enhanced by the ARBOs and/or individual entrepreneurs. An additional opportunity for tweaking the VLFED project to become nutrition-sensitive may also be done through the application of food fortification technology to their food processing centers to improve nutritional quality, increasing the availability of fortified food products the Province.

The nutrition-sensitive VLFED project will be able to improve the agriculture and economic situation of the community while at the same time improving the overall food security of the targeted poor households. Such project will provide additional income to poor households which can be used to provide the daily nutritional needs of the family members, especially the nutritionally-vulnerable which include pregnant and lactating women, infants and children aged 6-23 mos. In addition, nutrition education along with continuous follow-up and monitoring by the Barangay Nutrition Scholar/s will ensure that the increase in income is translated into good nutrition practices in the targeted households, leading to improved food security and overall nutritional status in the Province.

- Project Objectives

In all VLFED projects in the constituent municipalities and cities of the Province of __________, incorporate nutritional considerations through the inclusion of beneficiaries from food insecure and nutritionally vulnerable households within agrarian reform beneficiary organizations (ARBOs) who will receive livelihood trainings and assistance that provide for increased income, which together with provision of nutrition education, enhance their knowledge, skills, and practices on proper nutrition, and facilitate the improvement of food security and nutritional status of children in the beneficiary households.

- Project Outputs

- All VLFED projects in the constituent municipalities and cities of the Province apply nutritional considerations by selecting beneficiary households within agrarian reform communities (ARC) who are identified as food insecure and nutritionally-vulnerable

- At least 80% of ARBO-managed enterprises within the Province are able to secure applicable regulatory permits/licenses such as Food and Drug Administration – License to Operate (FDA-LTO) and Certificate of Product Registration (CPR) for processed food products, Environmental Compliance Certificate (ECC) for non-food products and other regulatory requirements for the commercial distribution of their products, including compliance to OSH standards

- A system to ensure adequate nutrition education and mentoring of all families involved in the nutrition-sensitive CPWASH project is established and fully operational resulting in effective coaching and mentoring on maternal and infant and young child nutrition and proper meal management within households

- At least 85% of VLFED beneficiaries have enhanced knowledge, skills, and practices on maternal and infant and young child nutrition, and have improved levels of food security and nutritional status of children of these households

- At least 85% of VLFED beneficiaries have enhanced knowledge, skills, and practices on maternal and infant and young child nutrition, and have improved levels of food security and nutritional status of children of these households

- The Province have issued local policies institutionalizing nutrition-sensitive VLFED and other related nutrition-sensitive projects

- Project Major Activities and Implementation Schedule

The project consists of five major activities that is implemented sequentially as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Consultative meetings and forging of agreements between DAR RO, PNO, and other stakeholders relevant to implementation, site assessment and validation | January 2020 |
| 2 | Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | January 2020 |
| 3 | Implementation of the project | February 2020 |
| 4 | Nutrition education to beneficiaries, follow-up, and monitoring by BNS | February 2020, regularly conducted to 2022 |
| 5 | First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | August 2020 onwards to 2020 |

- Project Management and Organization

The project is led by the Provincial Planning and Development Office with support from the Department of Agrarian Reform Regional Office. The Provincial Nutrition Office and the Local Nutrition Committees will take the lead in identifying the project beneficiaries, provide support in follow-up, and assist in project monitoring. Project implementation status, issues, and concerns will be discussed in the Local Nutrition Committees for remedial actions.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| Consultative meetings and forging of agreements between DAR RO, PNO, and other stakeholders relevant to implementation, site assessment and validation | DAR-RO, PPDO, PNO |  |  |  |  |
| Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | DAR-RO, PNO |  |  |  |  |
| Implementation of the project | DAR-RO |  |  |  |  |
| Nutrition education to beneficiaries, follow-up, and monitoring by BNS | PNO |  |  |  |  |
| First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | DAR RO, PNO |  |  |  |  |