# PROJECT BRIEF #6

| Project Title: | DOLE Integrated Livelihood and Emergency and Employment Program (DILEEP) |
| --- | --- |
| Project Location: | Province-wide |
| Proponent: | Provincial Government of _______________ |
| Implementing Agency: | Department of Labor and Employment Regional Office (DOLE RO) Province Nutrition Office |
| Start Date and Duration: | June 2020 to December 2022 |
| Beneficiaries: | Disadvantaged, food insecure, and nutritionally vulnerable households |
| Total Project Cost: | Php. xx,xxx,xxx |

- Rationale

The nutrition-sensitive program consists of a set of projects implemented by various local, regional, and national government agencies, with key participation of the Local Government Units, that have objectives other than nutritional and are redesigned to contribute to the achievement of nutritional outcomes by addressing underlying determinants of maternal, fetal, infant, and child nutrition and development, such as those pertaining to food security, social protection, adequate caregiving resources at the maternal household and community levels; access to health services and a safe and hygienic environment, and incorporate specific nutrition goals and actions. Nutrition-sensitive programs can serve as delivery platforms for nutrition-specific interventions, potentially increasing their scale, coverage, and effectiveness.

One of the projects identified under the nutrition-sensitive program is the DOLE Integrated Livelihood and Emergency Employment Programs (DILEEP) implemented by the Department of Labor and Employment (DOLE), through the Bureau of Workers with Special Concerns (BWSC) to contribute to poverty reduction and reduce the vulnerability to risks of the working poor, vulnerabl,e and marginalized workers through employment assistance and enterprise development.  In tweaking DILEEP to become nutrition-sensitive, priority shall be given to food insecure and nutritionally-vulnerable households within Agrarian Reform Communities (ARCs) who will also be receiving adequate nutrition education and mentoring on maternal and infant and young child nutrition and proper meal management within households.

According to the latest data, poverty incidence in the Province of ____________ stands at ___%, totaling into an estimated number of ____ households who are expected to benefit from employment assistance, and the promotion of entrepreneurship and community enterprises. Eligible projects that the identified beneficiaries can venture include those in line with the priorities of the Regional Development Council (RDC), Regional Convergence Committee (RCC) & development plan of LGUs. Industries identified as key employment generators (i.e. agribusiness, information technology, health and wellness, wholesale and retail trade, tourism, etc.) and DTI priority products (i.e. food processing, cacao, coffee, coco coir, wearable and home styles).

Such forms of assistance shall be provided to beneficiaries by the nutrition-sensitive DILEEP project to secure increases in income among the identified food insecure and nutritionally-vulnerable households, providing them with an improved capacity to buy food of sufficient quality and quantity, which along with the received nutrition education, would secure the overall improvement of nutritional status in the Province.

- Project Objectives

In all DILEEP projects in the Province of __________ from period 2020 to 2022, apply nutritional considerations through the inclusion of beneficiaries coming from locally identified food insecure and nutritionally vulnerable families for the provision of employment and livelihood assistance that provide for increased income, which together with enhanced knowledge, skills, and practices on proper nutrition, facilitate improved food security and nutritional status of children of these households.

- Project Outputs

- All DILEEP projects in all constituent municipalities and cities of the province apply nutritional considerations by selecting beneficiary households who are identified as food insecure and nutritionally-vulnerable

- A system to ensure adequate nutrition education and mentoring of all families involved in the nutrition-sensitive DILEEP in the Province is established and fully operational resulting in effective coaching and mentoring on maternal and infant and young child nutrition and proper meal management within households

- At least 85% of the DILEEP beneficiaries have enhanced knowledge, skills, and practices on maternal and infant and young child nutrition, and have improved levels of food security and nutritional status of children of these households

- The Province have issued local policies institutionalizing nutrition-sensitive DILEEP and other related nutrition-sensitive projects

- Project Major Activities and Implementation Schedule

The project consists of five major activities that are implemented sequentially as shown in Table 1 below.

Table 1. Activities and Timetable

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Consultative meetings between the DOLE RO and PNO, and other stakeholders relevant to the implementation | January 2020 |
| 2 | Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | January 2020 |
| 3 | Implementation of the project | February 2020 – March 2020 |
| 4 | Nutrition education to beneficiaries, follow-up, and monitoring by BNS | February 2020, regularly conducted to 2022 |
| 5 | First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | June 2020 and onwards |

- Project Management and Organization

The project is led by the DOLE Regional Office. The Provincial Nutrition Office and the Local Nutrition Committees will take the lead in identifying the project beneficiaries, support in follow-up, and assist in project monitoring. Project implementation status, issues, and concerns will be discussed in the Local Nutrition Committees for remedial actions.

- Estimates of Budgetary Requirements

The total estimated cost requirements of the initiative for the three-year implementation (2020-2022) amounts to P___________ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| Activity | Agency/ies Responsible | Budgetary Requirements |  |  | Source of Funds |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| Consultative meetings between the DOLE RO and PNO, and other stakeholders relevant to the implementation | DOLE-RO, PNO |  |  |  |  |
| Selection/identification of beneficiaries prioritizing those belonging to food insecure and nutritionally disadvantaged families | PNO |  |  |  |  |
| Implementation of the project | DOLE-RO |  |  |  |  |
| Nutrition education to beneficiaries, follow-up, and monitoring by BNS | PNO |  |  |  |  |
| First six months evaluation of results and continued follow-up, monitoring and adjustments to ensure expected outcomes | DOLE-RO, PNO |  |  |  |  |