PROJECT BRIEF

Project Title			: 	Enabling Program for Nutrition

Location			:	Municipal/City-wide

Implementing Agency		:	Municipal/City Nutrition Office

Start Date and Duration	: 	January 2020 to December 2022

Project Cost			:	P

I.	Rationale

The State recognizes the alarming state of malnutrition in the country.  The 2015 Updating of the National Nutrition Survey revealed that stunting stood at 33.4% affecting 4.6 million under-five years old; wasting among the same age group was estimated at 7.1% equivalent to about 1 million children while overweight and obesity for children was reported to be about 3.8% equivalent to 0.5 million children under-five years old. Malnutrition has significant negative consequences particularly in terms of poor health, lost human capital, and decreased economic productivity.  In recognition of this alarming state of malnutrition, current national policies declares the need for all sectors at all levels to work together in addressing all forms of malnutrition in the country particularly stunting.

The Philippine Plan of Action for Nutrition (PPAN) 2017-2022 identified focus provinces having the highest prevalence of stunting to be prioritized for nutrition program management to ensure achievement of planned outcomes. Based on the same survey, the stunting rate of Zamboanga del Norte is at 41.4% which is significantly higher than the national and regional averages (38%) affecting an estimated 56,526 children under-five year old.  The province tops the provinces in the Zamboanga Peninsula with the highest stunting prevalence.  The Municipality/City of ______ mirrors the nutrition situation of the province.

The PPAN calls for an Enabling Program that supports nutrition-specific programs  to be achieved with greater degree of efficiency and effectiveness.  In order to contribute to the achievement of PPAN outcomes, the Municipality/City of _______________ should be able to 1) mobilize the local government unit up to the level of the barangay to implement nutrition programs of sufficient scale and quality, facilitate the convergence of services which will require the engagement and involvement of national government agencies, the Municipal/City government, and the sectoral units and other partner agencies of the barangays, 2) create an enabling policy environment for food and nutrition in the municipality/city, and 3) strengthening management support to facilitate improved program management and coordination and ensure the activation of the Local Nutrition Committees as well as key critical program implementers and community nutrition workers/volunteers as the Municipality/City of _________ gears toward delivering sustained positive nutrition outcomes.

II. Program Objectives

- Strengthen management support for the effective implementation of the Local Nutrition Action Plan

  - Establish/strengthen the Municipal/City Nutrition Committee, which also serves as the Municipal/City Nutrition Cluster, to effectively coordinate and manage the implementation of nutrition programs during normal and emergency situations in the city/municipality

  - Strengthen the coordination, management, monitoring and evaluation of the Municipal/City Nutrition Action Plan 2020-2022

  - Support the continuing education, full capacitation, and deployment of barangay level health and nutrition workers for quality periodic nutritional assessment of children (Operation Timbang Plus) and follow up

- Mobilize the municipal/city and constituent barangays for effective implementation of programs for the achievement of nutrition outcomes

  - Increase the level of understanding and political support of all members of the Sanggunian and all the Punong Barangay on the rationale of investing in nutrition particularly on the first 1,000 days through capacity building conducted with local nutrition committees and conduct of learning exchange/visits to performing LGUs in nutrition

  - Increase the number/percentage of constituent barangays moving up one notch higher in the local nutrition committee functionality scale and develop and implement an incentives and awards system for well performing barangays and local implementers for nutrition

  - Provide supportive supervision within the LGU and all constituent barangays on local nutrition planning and in integrating nutrition and the first 1000 days in major local plans and budgets such as in the Comprehensive Development Plans (CDP), Local Development Investment Programs (LDIP), and the Annual Investment Program (AIP), as well as in the functionality of local nutrition committees

- Create an enabling policy environment for food and nutrition in the local government unit

  - Undertake the review and updating of existing local policies towards improved food and nutrition in the municipality/city and all constituent barangays

  - Build and strengthen the capacities of the municipality/city and all its constituent barangays along policy development for food and nutrition and advocate for the development, passage and implementation of local policies and legislations supporting the first 1000 days and those related to food and nutrition, within the municipality/city and in all constituent barangays

III.	Program Outputs

- Management support in place and strengthened for the effective implementation of the Local Nutrition Action Plan

  - A Municipal/City Nutrition Office reinforced/established and fit to the requirements of the Municipal/City Nutrition Action Plan being manned by full time Municipal/City Nutrition Action Officer and staff with sufficient budgetary support with relevant Technical Working Groups created within the Municipal/City Nutrition Committee/ Municipal/City Nutrition Cluster

  - A fully functional Municipal/City Nutrition Committee/Nutrition Cluster capable of effectively coordinating, managing, monitoring and evaluating the Municipal/City Nutrition Action Plan 2020-2022

  - Support provided for the continuing education, full capacitation, and deployment of barangay health and nutrition workers for periodic nutrition assessment (Conduct of Operation Timbang Plus) and their routine provision of health and nutrition services

- Municipality/city and constituent barangays mobilized for the effective implementation of programs for the achievement of nutrition outcomes

  - All members of the Sanggunian and Punong Barangays are covered by advocacy/interface activities towards increased understanding the rationale of investing in nutrition particularly on the first 1,000 days and in providing leadership for scaled-up nutrition action and conducted learning exchange/visits to performing LGUs in nutrition

  - Increase the number/percentage of constituent barangays that have a functional local nutrition committee as measured by the local nutrition committee functionality scale with well performing barangays and nutrition program implementers recognized and provided incentives through an incentives and awards system on nutrition

  - Capacity building and training undertaken by the LGU and its constituent barangays leading to nutrition and the first 1,000 days being integrated in the local development plans and budgets such as the Comprehensive Development Plan (CDP), Executive-Legislative Agenda (ELA), Local Development Investment Program (LDIP), Annual Investment Program (AIP), other sectoral plans of the municipality/city, as well as in the Barangay Development Plans of constituent barangays

- Enabling policy environment for food and nutrition created within the local government unit and constituent barangays

  - Existing local policies towards improved food and nutrition in the municipality/city and all constituent barangays reviewed and updated during capacity building trainings and meetings for policy development for food and nutrition

  - Increase in the number of local policies supporting food and nutrition developed, updated, passed and implemented by the municipality/city and adopted by all its constituent barangays

IV.	Program Major Activities and Implementation Schedule

The Enabling Program of the Municipality/City of _________ for the first 1000 days and delivery of nutritional outcomes consists of the following major activities as shown in the table  below.

| # | Major Activities | Timetable |
| --- | --- | --- |
| 1 | Securing approval and funding for the project | January 2020 |
| 2 | Hiring/Designation of a full time Municipal/City Nutrition Action Officer and nutrition staff | January 2020 |
| 3 | Establishing/Strengthening of the Municipal/City Nutrition Office with full funding for its operations | January 2020 |
| 4 | Conduct of consultative and planning meetings with internal and external project stakeholders and with the LCE and nutrition teams | January 2020 and continuing up to 2022 |
| 5 | Conduct of advocacy/interface activities with the members of the Sanggunian, the Local Nutrition Committee, and all Punong Barangays on the rationale of investing in nutrition for scaled up nutrition action in the municipality/city | January 2020 |
| 6 | Conduct of capacity building programs including learning exchange/visit with performing LGUs on First 1000 Days and nutrition programming (e.g. Quezon Province Q1K Program) | February 2020 |
| 7 | Issuance of an Executive Order from the Local Chief Executive to end all forms of malnutrition in the municipality/city and its constituent barangays with policy issuance to include the creation of the First 1000 Days program in the municipality/city and all its related activities | January to February 2020 |
| 8 | Conduct of planning workshop on integrating nutrition in the Annual Investment Program (AIP) of the municipality/city with the local nutrition committee, municipal/city nutrition office, and other key stakeholders in the LGU | February 2020 |
| 9 | Undertake the review of existing policies, legislations, other policy guidelines relevant to food and nutrition, LGU compliance to service standards around the first 1,000 days and integrate results of such review in LGU, RHU, and agency plans and operations | February 2020 and continuing up to 2022 |
| 10 | Conduct of capacity building among key players on policy development for food and nutrition and management of nutrition/F1K champions in the LGU and in the barangays as LGU mobilizers | March 2020 and continuing to October 2022 |
| 11 | Conduct of staff development activities for the M/CNC, M/CNO and health and nutrition workers on nutrition program management, F1K, nutrition in emergencies and other technical updates | March 2020 and continuing to October 2022 |
| 12 | Provision of support for the continuing education, capacity development, and full deployment of BNS and BHWs for periodic nutrition assessment (OPT Plus) | 2020 to 2022 |
| 13 | Documentation, compilation, and dissemination of good practices/actions on nutrition and the first 1000 days | June 2020 and annually up to 2022 |
| 14 | Provision of incentives and awards for performing barangays and community workers and volunteers in nutrition programming | December 2020 and annually up to 2022 |
| 15 | Conduct of compliance monitoring on F1K, food fortification and other programs, projects and activities included in the M/CNAP during the annual PIR, and end-of-plan evaluation for adjustments, scaling up, and re-planning | 2020 to 2022 |

V.	Project Management and Organization

Project implementation and management will be spearheaded by the Municipal/City Nutrition Office (M/CNO). As project lead, the M/CNO will convene the meetings and other activities necessary to coordinate and manage the project as a whole. It shall ensure the active participation of the Sanggunian and other sectoral agencies including the DILG Municipal/City Office and the barangays.  The Municipal/City Nutrition Committee shall serve as the oversight structure for the implementation of the project.

The M/CNO shall report to the Municipal/City Nutrition Committee the status of project implementation and important lessons that can guide the planning and implementation for the coming year.

VI.	Estimates of Budgetary Requirements

The total estimated cost requirements for the three-year project implementation (2020-2022) amounts to P _______ broken down by activity as follows:

Table 2. Estimates of Budgetary Requirements by Activity, by Year and Source of Funds

| # | Activity | Agency Responsible | Budgetary Requirements |  |  | Fund Source |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2020 | 2021 | 2022 |  |
| 1 | Hiring/Designation of a full time Municipal/City Nutrition Action Officer and nutrition staff | M/CNO |  |  |  |  |
| 2 | Establishing/Strengthening of the Municipal/City Nutrition Office with full funding for its operations | M/CNO |  |  |  |  |
| 3 | Conduct of consultative and planning meetings with internal and external project stakeholders and with the LCE and nutrition teams | M/CNO |  |  |  |  |
| 4 | Conduct of advocacy/interface activities with the members of the Sanggunian, the Local Nutrition Committee, and all Punong Barangays on the rationale of investing in nutrition for scaled up nutrition action in the municipality/city | M/CNO |  |  |  |  |
| 5 | Conduct of capacity building programs including learning exchange/visit with performing LGUs on First 1000 Days and nutrition programming (e.g. Quezon Province Q1K Program) | M/CNO, Office of the Mayor |  |  |  |  |
| 6 | Issuance of an Executive Order from the LCE to end all forms of malnutrition in the municipality/city and its constituent barangays with policy issuance to include the creation of the First 1000 Days program in the municipality/city and all its related activities | M/CNO, M/CNC |  |  |  |  |
| 7 | Conduct of planning workshop on integrating nutrition in the Annual Investment Program (AIP) of the municipality/city with the local nutrition committee, municipal/city nutrition office, and other key stakeholders | M/CNO |  |  |  |  |
| 8 | Undertake the review of existing policies, legislations, other policy guidelines relevant to food and nutrition, LGU compliance to service standards around the first 1,000 days and integrate results of such review in LGU, RHU, and agency plans and operations | M/CNO with C/MPDO and C/MHO |  |  |  |  |
| 9 | Conduct of capacity building among key players on policy development for food and nutrition and management of nutrition/F1K champions in the LGU and in the barangays as LGU mobilizers | M/CNO with C/MPDO |  |  |  |  |
| 10 | Conduct of staff development activities for the M/CNC, M/CNO and health and nutrition workers on nutrition program management, F1K, nutrition in emergencies and other technical updates | M/CNO and M/CHO |  |  |  |  |
| 11 | Provision of support for the continuing education, capacity development, and full deployment of BNS and BHWs for periodic nutrition assessment (OPT Plus) | M/CNO |  |  |  |  |
| 12 | Documentation, compilation, and dissemination of good practices/actions on nutrition and the first 1000 days | M/CNO |  |  |  |  |
| 13 | Provision of incentives and awards for performing barangays and community workers and volunteers in nutrition programming | Mayor’s Office |  |  |  |  |
| 14 | Conduct of compliance monitoring on F1K, food fortification and other programs, projects and activities included in the M/CNAP during the annual PIR, and end-of-plan evaluation for adjustments, scaling up, and re-planning | M/CNO, M/CHO |  |  |  |  |

Stunting is the result of long-term nutritional deprivation and often results in delayed mental development, poor school performance and reduced intellectual capacity.

These national policies include the Philippine Development Plan and the Philippine Plan of Action for Nutrition (PPAN) 2017-2022, Republic Act 11037: “Masustansyang Pagkain para sa Batang Pilipino Act”, Republic Act 11148: “Kalusugan at Nutrisyon ng Mag-Nanay Act”, among others.

These are interventions or programs that address the immediate determinants of maternal, fetal, infant and child nutrition and development and low burden of infectious diseases

Nutrition programs would include the PPAN-based nutrition specific, nutrition sensitive and enabling programs

Functionality of Local Nutrition Committees is determined using the Guidelines on Establishing a Database on Functional Nutrition Committees developed by NNC and supported by DILG Memorandum Circular 2015-19 issued on 26 February 2015

Functionality of Local Nutrition Committees is determined using the Guidelines on Establishing a Database on Functional Nutrition Committees developed by NNC and supported by DILG Memorandum Circular 2015-19 issued on 26 February 2015

NNC will provide all provinces with a compendium and facsimile of local legislations and ordinances that have improved nutrition programming in performing LGUs